## Sheet1
Design FMEA
Project | Robot Power | [6 empty] | Version | 2
Sub assembly | [7 empty] | Date | 2024-06-12
Prepared by | Zakariyyaa Chachia | [6 empty] | Page____ of ______
Approved by | [7 empty] | Notes
Process Purpose | Potential Failure Mode | Severity | Potential Causes of Failure | Occurrence | Process Control | Detection | RPN | Recommended Actions | Area / person responsible | Delivery date | Action taken | Severity | Occurrence | Detection | New RPN
Regulate Voltage to < 3.3V | Exceeds 3.3V | 8 | DC offset might be too high / spike Too large of a differ~ence in the input voltages | 2 | Voltage reading from ADC | 1 | 16 | Redesign amplifier circuit, and test robustly | Power and Sensors - Mehwish and Rayaan | 2024-06-17 | N/A | - | - | - | -
Measuring distance value | If the bot gets too close, the value given will no longer be correct | 5 | Control System overshoots and we get too close | 7 | Measured via microcontroller | 7 | 245 | Include logic to stop the robot if it gets too close to an obstacle (before this failure can occur) | Control System - Zakariyyaa Communication - Matteusz | 2024-06-17 | N/A | - | - | - | -
Balance Controller | Bot will oscillate too heavily and fall | 8 | PID values not tuned enough External force acting on the bot Setpoint is given incorrectly | 5 | Measured via observation | 8 | 320 | Finely tune PID values to ensure all oscillations are damped accordingly | Control System - Zakariyyaa | 2024-06-17 | PID values tuned correctly | 2 | 2 | 4 | 16
Balance Controller | Robot will be stable, but still fall | 8 | The data from the MPU is corrupted by high currents from the batteries | 6 | Measured via observation | 8 | 384 | Keep battery cables sufficiently away from the MPU to reduce the risk of this error | Control System - Zakariyyaa | 2024-06-17 | Cables ziptied to opposing side of the underbelly of the robot | 2 | 2 | 8 | 32
Balance Controller | Speed set too high, causing instability and potential falling | 7 | User error | 5 | Measured via observation | 6 | 210 | Have an upper limit for the allowable speed of the robot to ensure this error does not occur | Control System - Zakariyyaa | 2024-06-17 | Specific speed values chosen to ensure that this issue cannot occur | 1 | 3 | 6 | 18